## Test Plan
Task | Description | Priority | Estimated Time (day)
Requirement Analysis and Test Planning | -Review the website to understand its functionalities. -Identify test scenarios and create a test plan. | High | 0.5
Setup Test Environment | -Set up necessary test environments, including browsers and devices. -Configure any required tools (e.g., automated testing tools). | Medium | 0.5
Functional Testing | Test core functionalities like browsing products, adding items to the cart, checking out, and user management. | High | 2
Regression Testing | -Re-test the entire website after bug fixes or updates to ensure that no new issues were introduced. | Medium | 1
Test Reporting and Documentation | -Document test results, defects, and provide a final report. | Low | 1

## E2E Test Case
No. | Scenario | Pre-conditions | Test Steps | Expected Result | Automation | Test Result
TC001 | Successful Product Purchase | -User has access to the website | 1. Navigate to the website: https://www.demoblaze.com/index.html 2. Select the product from the Phone category list and adding to the cart. 3. Return to the Home page and select a product from the Laptops category list and adding to the cart. 4. Return to the Home page and select a product from the Monitor category list and adding to the cart. 5. Navigate to the Cart. 6. Delete the last product from the list. 7. Click the "Place Order" button. 8. Fill in the all information and click the "Purchase" button. 9. Click "Close" the window. | 1. The Home page is displayed and categorised by produce category. 2. The product from Phone category is displayed with information on the product details page and the user able to add the product into the cart successfully. 3. The product from Laptops category is displayed with information on the product details page and the user able to add the product into the cart successfully. 4. The product from Monitor category is displayed with information on the product details page and the user able to add the product into the cart successfully. 5. See all the added products are displayed on the Cart summary details page. 6. See the window for adding the purchase information. 7. See the last produce is removed from the updated cart. 8. Should see the popup window with successfully purchase message as "Thank you for your purchase" with the submitted purchase information correctly. 9. The page redirect to the Product listing page | Automatable
TC002 | Checkout with an Empty Cart | -User has access to the website | 1. Navigate to the website: https://www.demoblaze.com/index.html 2. Navigate to the Cart. 3. Click "Place Order" | 1. User should receive a warning message that the cart is empty and cannot proceed. | Automatable
TC003 | Network Interruption During Checkout | -User has access to the website | 1. Navigate to the website: https://www.demoblaze.com/index.html 2. Navigate to the Cart. 3. Click "Place Order" | 1. The system should handle the error gracefully, allowing the user to retry the transaction or receive an appropriate error message. | Manual
TC004 | Incorrect Shipping Information | -User has access to the website | 1. Navigate to the website: https://www.demoblaze.com/index.html 2. Select the product from the Phone category list and adding to the cart. 3. Navigate to the Cart. 4. Click "Place Order" 5. Enter with invalid card number. | 1. The system should not allow the user to proceed until the shipping information is corrected. | Manual